## Template
Project Plan Template
There are multiple sheets within this tool—click through the tabs at the bottom of the spreadsheet. For our best thinking and tips on each section, hover over or click on cells with a small triangle bookmark at the top right.
Project Name: | [5 empty] | Timeline: | [17 empty] | T 2 | [16 empty] | T 3
Success Looks Like: | [5 empty] | Stakeholders | [13 empty] | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46
[20 empty] | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30
Manager | Owner | Consulted | Helper | Approver |  | □ □ □ | [13 empty] | 2020-06-01: Reminder; 2020-06-08: Reminder; 2020-11-30: Important Date
Stream: | [5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Choice Points: | [5 empty] | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20
Step |  | Owner | Stakeholders/ Consulted | Due | Status | 2019-11-25: Holiday Week; 2019-12-02: Reminder; 2019-12-23: Important Date; 2019-12-30: Holiday Week
Step 1 |  |  |  |  | Done | bar: 2019-10-21
Step 2 |  |  |  |  | Working on it
Step 3 |  |  |  |  | Stuck
Step 4
Step 5
Step 6
Step 7
Step 8
Step 9
Step 10
Stream:
Choice Points:
Step |  | Owner | Stakeholders/ Consulted | Due | Status
Stream:
Choice Points:
Step |  | Owner | Stakeholders/ Consulted | Due | Status
Note on A8: Start by communicating what success looks like at the end of the project. Tips: - A good success statement has quantity (e.g. specific numbers) and defines measures that are more qualitative. - Make the implicit explicit. - Consider choice points. - This statement is what you will use to evaluate your program's success. Does it make sense to measure these things?
Note on G8: Stakeholders could be the people most affected by the project, or people who will determine the success/failure of the project. Have them front, center, and visible. Throughout the process of the project, make sure you check in with these people. Refer to this list at the end of the project (for scheduling debriefs, sharing gratitude, or making acknowledgements).
Note on A11: Make the MOCHA visible. Share this spreadsheet with everyone in your MOCHA. Test your MOCHA by asking: - Is everyone aware of (and has consented to) their role in the MOCHA? - After you build the work plan: Does your MOCHA account for most people who will be involved in the project? Are there any invisible helpers or shadow approvers? (The goal is clarity, not 100% comprehensiveness.)
Note on G13: Based on the Gantt chart, this section lets you know at a glance how much time you have (whether it's in days or weeks). The colored blocks indicate the time allocated for a person to do the step. Tips: - Revisit as you go! As the work progresses, things will naturally shift. This lets you keep track of where you are (and where you might need more time). - Pay attention to how many blocks each person has per week.
Note on A14: Be proactive and identify opportunities to embed and promote racial equity and inclusion throughout your project.
Note on A15: Steps are the specific actions that make up the stream. Get specific and include buffers and mini mitigation plans. Tips: - Note differences between internal and must-achieve by/external deadlines. - Include getting input from stakeholders. - Your steps might have dependencies (a specific sequence in which they have to happen), so try to write them in chronological order. - If you anticipate risks, name them.
Note on C15: The person responsible for the success or failure of the step/task.
Note on D15: The person/people being reached out to for input, buy-in, or (sometimes) approval.
Note on E15: Start at the end (when you know the project needs to be done by), then work backwards.
Note on F15: Review this column at project update meetings. The "stuck" option is for flagging a need for help from someone else. Spend less time at meetings on updates and more time on mitigating roadblocks.
Note on G15: Use this row for important dates that may impact people's availability or capacity.

## Sample
Project Plan Sample
For our best thinking and tips on each section, hover over or click on cells with a small triangle bookmark at the top right.
Project Name: Panel on Climate Change Initiative | [5 empty] | Timeline: 10/22-1/15. Panel is 1/15. | [17 empty] | T 2 | [16 empty] | T 3
Success Looks Like: At least 80 participants attend the event, of which 75% share they are satisfied with the event and feel equipped to take action on the upcoming climate bills. People of Color and/or Indigenous (POCI) are at least as satisfied + strongly agree as non-POCI. | [5 empty] | Stakeholders | [13 empty] | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46
[20 empty] | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30
Manager | Owner | Consulted | Helper | Approver |  | □ Inez (Board Chair) □ Berniece (lead volunteer) □ Zein (logistics director) □ Vijay (assistant to keynote speaker) □ Retta (local activist) | [13 empty] | 2020-06-01: Reminder; 2020-06-08: Reminder; 2020-11-30: Important Date
Dan | Sue | Vijay Retta | Tina (RSVPs) John (Panel) Rachel (Comms) | Carlos
Stream: Panel Discussion | [5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Choice Points: Make sure speakers are representative of communities impacted; clearly share our equity and inclusion values with speakers; get input from Berniece and Retta on speaker selection. | [5 empty] | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20
Step |  | Owner | Stakeholders/ Consulted | Due | Status | 2019-11-25: Holiday Week; 2019-12-23: Holiday Week; 2019-12-30: Holiday Week
Draft outline of topics we want covered in discussion |  | John |  | 2019-10-28 | Done | bar: 2019-10-21 to 2019-10-28
Identify potential speakers to join the panel |  | Carlos | Carlos reaches out to Vijay to pitch keynote speaker | 2019-10-30 | Done | bar: 2019-10-28
Draft email invite for speakers |  | John |  | 2019-11-03 | Done | bar: 2019-10-28 to 2019-11-04
Carlos signs-off and sends email |  | John |  | 2019-11-07 | Done | bar: 2019-11-04 to 2019-11-11
Confirm speakers (internal deadline) and arrange call with speakers |  | John |  | 2019-11-17 | Done | bar: 2019-11-11 to 2019-11-18
Send speakers email: info on panelists, our publications, outline for discussion |  | John |  | 2019-11-20 | Working on it | bar: 2019-11-11 to 2019-11-18
Call with speakers · Dan, Carlos, John, Tina · Dec. 11, sm conf. room |  | John |  | 2019-12-08 | Working on it | bar: 2019-11-25 to 2019-12-09
Revise and send out final outline for discussion · Potential Risks: Approval process takes longer than expected · Mitigation: Agree on coding system for emails to quickly differentiate between FYIs, urgent requests, and “when you get a chance” input |  | John |  | 2019-12-15 | Stuck | bar: 2019-12-09 to 2019-12-16
Confirm speakers’ attendance; special requests if needed (must-have/external deadline) |  | John |  | 2019-12-18 | bar: 2019-12-09 to 2019-12-16
Host event! |  | John |  | 2020-01-15 | bar: 2020-01-20
Host a project debrief meeting with all involved and document learnings |  | John |  | 2020-01-20 | bar: 2020-01-20
Stream: Invitation
Choice Points: PTR flag! Don’t rely on last year’s invite list. CP: share venue accessibility and scholarship information in invite.
Step |  | Owner | Stakeholders/ Consulted | Due | Status
Brainstorm session with team re: how to get the word out |  | Rachel | Retta: talk about advertising and local scholarships | 2020-11-10 | Done | bar: 2019-10-28 to 2019-11-11
Draft invite |  | Rachel |  | 2020-11-19 | Working on it | bar: 2019-11-04 to 2019-11-11
Get comments from Dan on invite |  | Rachel |  | 2020-11-28 | Stuck | bar: 2019-11-18 to 2019-11-25
Revise invite based on Dan input |  | Rachel |  | 2020-12-07 | bar: 2019-12-02
Finalize and send out |  | Rachel |  | 2020-12-09 | bar: 2019-12-09
Track Respones |  | Tina |  | Throughout | bar: 2019-12-09 to 2019-12-30
Email reminder to RSVPs |  | Tina |  | 2020-01-06 | bar: 2019-12-30 to 2020-01-06
Stream: Materials
Choice Points: Ask for stakeholder input on program draft; review all materials for uninclusive language.
Step |  | Owner | Stakeholders/ Consulted | Due | Status
Draft program and inserts |  | Sue | Vijay: recommends looking at '18 program | 2020-11-20 | Working on it | bar: 2019-11-11 to 2019-11-18
Send materials to Dan |  | Sue |  | 2020-11-20 | Working on it | bar: 2019-11-11 to 2019-11-18
Revise materials based on Dan input |  | Sue |  | 2020-12-12 | bar: 2019-12-09 to 2019-12-16
Finalize and make copies |  | Tina | Use heavy paper | 2020-12-17 | bar: 2019-12-16
Note on A8: Start by communicating what success looks like at the end of the project. Tips: - A good success statement has quantity (e.g. specific numbers) and defines measures that are more qualitative. - Make the implicit explicit. - Consider choice points. - This statement is what you will use to evaluate your program's success. Does it make sense to measure these things?
Note on G8: Stakeholders could be the people most affected by the project, or people who will determine the success/failure of the project. Have them front, center, and visible. Throughout the process of the project, make sure you check in with these people. Refer to this list at the end of the project (for scheduling debriefs, sharing gratitude, or making acknowledgements).
Note on A11: Make the MOCHA visible. Share this spreadsheet with everyone in your MOCHA. Test your MOCHA by asking: - Is everyone aware of (and has consented to) their role in the MOCHA? - After you build the work plan: Does your MOCHA account for most people who will be involved in the project? Are there any invisible helpers or shadow approvers? (The goal is clarity, not 100% comprehensiveness.)
Note on G14: Based on the Gantt chart, this section lets you know at a glance how much time you have (whether it's in days or weeks). The colored blocks indicate the time allocated for a person to do the step. Tips: - Revisit as you go! As the work progresses, things will naturally shift. This lets you keep track of where you are (and where you might need more time). - Pay attention to how many blocks each person has per week.
Note on A15: Be proactive and identify opportunities to embed and promote racial equity and inclusion throughout your project.
Note on A16: Steps are the specific actions that make up the stream. Get specific and include buffers and mini mitigation plans. Tips: - Note differences between internal and must-achieve by/external deadlines. - Include getting input from stakeholders. - Your steps might have dependencies (a specific sequence in which they have to happen), so try to write them in chronological order. - If you anticipate risks, name them.
Note on C16: The person responsible for the success or failure of the step/task.
Note on D16: The person/people being reached out to for input, buy-in, or (sometimes) approval.
Note on E16: Start at the end (when you know the project needs to be done by), then work backwards.
Note on F16: Review this column at project update meetings. The "stuck" option is for flagging a need for help from someone else. Spend less time at meetings on updates and more time on mitigating roadblocks.
Note on G16: Use this row for important dates that may impact people's availability or capacity.