## Template
Project Plan Template
Project Name: | [6 empty] | Timeline: | [17 empty] | T 2 | [16 empty] | T 3
Success Looks Like: | [6 empty] | Stakeholders | [13 empty] | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46
[21 empty] | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30
Manager | Owner | Consulted | Helper | Approver |  |  | } } } } | [13 empty] | 2020-06-01: Reminder; 2020-06-08: Reminder; 2020-11-30: Important Date
Workstream: | [6 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
[7 empty] | 2025-01-01 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-29 | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02
Step |  | Owner | Stakeholders/ Consulted | Start | Due | Status | 2025-01-01: Holiday Week; 2025-02-12: Reminder; 2025-03-05: Important Date; 2025-03-12: Holiday Week
Step 1 | [6 empty] | 2025-01-15: 2024-11-06
Step 2
Step 3
Step 4
Step 5
Step 6
Step 7
Step 8
Step 9
Step 10
Workstream:
Step |  | Owner | Stakeholders/ Consulted | Start | Due | Status
Workstream:
Step |  | Owner | Stakeholders/ Consulted | Start | Due | Status
© 2025 The Management Center
Note on A4: Start by communicating what success looks like at the end of the project. Tips: - A good success statement has quantity (e.g. specific numbers) and defines measures that are more qualitative. - Make the implicit explicit. - Consider choice points. - This statement is what you will use to evaluate your program's success. Does it make sense to measure these things?
Note on H4: Stakeholders could be the people most affected by the project, or people who will determine the success/failure of the project. Have them front, center, and visible. Throughout the process of the project, make sure you check in with these people. Refer to this list at the end of the project (for scheduling debriefs, sharing gratitude, or making acknowledgements).
Note on A7: Make the MOCHA visible. Share this spreadsheet with everyone in your MOCHA. Test your MOCHA by asking: - Is everyone aware of (and has consented to) their role in the MOCHA? - After you build the work plan: Does your MOCHA account for most people who will be involved in the project? Are there any invisible helpers or shadow approvers? (The goal is clarity, not 100% comprehensiveness.)
Note on H9: Based on the Gantt chart, this section lets you know at a glance how much time you have (whether it's in days or weeks). The colored blocks indicate the time allocated for a person to do the step. Tips: - Revisit as you go! As the work progresses, things will naturally shift. This lets you keep track of where you are (and where you might need more time). - Pay attention to how many blocks each person has per week.
Note on A11: Steps are the specific actions that make up the stream. Get specific and include buffers and mini mitigation plans. Tips: - Note differences between internal and must-achieve by/external deadlines. - Include getting input from stakeholders. - Your steps might have dependencies (a specific sequence in which they have to happen), so try to write them in chronological order. - If you anticipate risks, name them.
Note on C11: The person responsible for the success or failure of the step/task.
Note on D11: The person/people being reached out to for input, buy-in, or (sometimes) approval.
Note on F11: Start at the end (when you know the project needs to be done by), then work backwards.
Note on G11: Review this column at project update meetings. The "stuck" option is for flagging a need for help from someone else. Spend less time at meetings on updates and more time on mitigating roadblocks.
Note on H11: Use this row for important dates that may impact people's availability or capacity.

## Sample - KYR Campaign
Project Plan Template
Project Name: | [6 empty] | Timeline: | [17 empty] | T 2 | [16 empty] | T 3
Success Looks Like: CARE will host #10 information sessions for advocates, schools, and nonprofits around the state. Sessions will be 1 hour; virtual and in-person. The program will show public support for queer youth and facilitate information about the law's policy implications with advocates. | [6 empty] | Stakeholders | [13 empty] | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46
[21 empty] | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30
Manager | Owner | Consulted | Helper | Approver |  |  | □ □ □ □ □ | [13 empty] | 2020-06-01: Reminder; 2020-06-08: Reminder; 2020-11-30: Important Date
Andrew | Janelle | Gail | Kyung (Marketing and communications) Sam (Programming) Marielena (Logistics) Tony (Engagement) | Chloe
Workstream: Communications | [6 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
[7 empty] | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-06
Step |  | Owner | Stakeholders/ Consulted | Start | Due | Status | 2025-03-12: Holiday Week; 2025-03-19: Reminder; 2025-04-09: Important Date; 2025-04-16: Holiday Week
Develop messaging strategy |  | Kyung |  | 2025-02-12 | 2025-02-28 | Working on it | 2025-02-26: 2025-02-28
Create branding materials |  | Kyung | Luis (social media) | 2025-03-05 | 2025-03-07 | Working on it | bar: 2025-03-05
Design promotional materials |  | Kyung | Luis (social media) | 2025-03-07 | 2025-03-17 | bar: 2025-03-05 to 2025-03-12
Develop press release and media kit |  | Kyung | Didra, Coalition Table | 2025-03-14 | 2025-04-11 | bar: 2025-03-05 to 2025-04-09
Set up registration system (depend on XYZ) |  | Kyung | Carlota (Comms Ops) | 2025-03-14 | 2025-03-21 | bar: 2025-03-12 to 2025-03-19
Create social media campaign calendar |  | Kyung | Luis (social media) | 2025-03-23 | 2025-03-28 | bar: 2025-03-19 to 2025-03-26
Draft email communications template |  | Kyung |  | 2025-03-22 | 2025-04-04 | bar: 2025-04-02
Create feedback surveys |  | Kyung |  | 2025-04-16 | 2025-04-18 | bar: 2025-04-16
Workstream: Community Engagement | [6 empty] | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-06
Step |  | Owner | Stakeholders/ Consulted | Start | Due | Status
Identify target communities and organizations |  | Tony | Didra, Coaliton Table | 2025-02-12 | 2025-02-24 | Done | bar: 2025-02-12 to 2025-02-19
Create stakeholder database |  | Tony |  | 2025-02-23 | 2025-02-28 | Done | bar: 2025-02-19 to 2025-02-26
Develop outreach strategy |  | Tony | Didra, Coaliton Table | 2025-03-05 | 2025-03-07 | bar: 2025-03-05
Create community feedback mechanisms |  | Tony |  | 2025-03-12 | 2025-04-18 | bar: 2025-03-12 to 2025-04-16
Schedule preliminary meetings with key partners |  | Tony |  | 2025-03-19 | 2025-03-24 | bar: 2025-03-19 to 2025-03-26
Train advocate volunteers |  | Tony | Sam | 2025-04-11 | 2025-04-11 | bar: 2025-04-09
Establish ongoing communication channels |  | Tony | Kyung | 2025-04-17 | 2025-04-25 | bar: 2025-04-16 to 2025-04-23
Develop follow-up engagement plan |  | Tony | Coalition Table | 2025-04-17 | 2025-04-30 | bar: 2025-04-16 to 2025-04-30
Workstream: Logistics | [6 empty] | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16 | 2025-04-23 | 2025-04-30 | 2025-05-06
Step |  | Owner | Stakeholders/ Consulted | Start | Due | Status
Research venues |  | Marielena | Sam (programming) | 2025-02-14 | 2025-02-24 | Done | bar: 2025-02-12 to 2025-02-26
Create selection criteria for venues |  | Marielena |  | 2025-02-25 | 2025-02-27 | Stuck | bar: 2025-02-26
Create budget for venues |  | Marielena | Hector (accounting) | 2025-02-26 | 2025-02-28 | Working on it | bar: 2025-02-26
Site visits |  | Marielena |  | 2025-02-26 | 2025-03-07 | Working on it | bar: 2025-02-26 to 2025-03-05
Plan setup and support needs |  | Marielena |  | 2025-03-07 | 2025-04-04 | bar: 2025-02-26 to 2025-04-02
Andrew reviews and approves selection criteria |  | Marielena | Andrew | 2025-03-12 | 2025-03-12 | bar: 2025-03-12
Review Meeting: Compare venue options |  | Marielena |  | 2025-03-20 | 2025-03-21 | bar: 2025-03-19
Book venues |  | Marielena |  | 2025-03-21 | 2025-03-21 | bar: 2025-03-19
Confirm venue payment/processing with Finance |  | Marielena | Hector (accounting) | 2025-03-21 | 2025-03-28 | bar: 2025-03-19 to 2025-03-26
©2025 The Management Center
Note on A4: Start by communicating what success looks like at the end of the project. Tips: - A good success statement has quantity (e.g. specific numbers) and defines measures that are more qualitative. - Make the implicit explicit. - Consider choice points. - This statement is what you will use to evaluate your program's success. Does it make sense to measure these things?
Note on H4: Stakeholders could be the people most affected by the project, or people who will determine the success/failure of the project. Have them front, center, and visible. Throughout the process of the project, make sure you check in with these people. Refer to this list at the end of the project (for scheduling debriefs, sharing gratitude, or making acknowledgements).
Note on A7: Make the MOCHA visible. Share this spreadsheet with everyone in your MOCHA. Test your MOCHA by asking: - Is everyone aware of (and has consented to) their role in the MOCHA? - After you build the work plan: Does your MOCHA account for most people who will be involved in the project? Are there any invisible helpers or shadow approvers? (The goal is clarity, not 100% comprehensiveness.)
Note on H9: Based on the Gantt chart, this section lets you know at a glance how much time you have (whether it's in days or weeks). The colored blocks indicate the time allocated for a person to do the step. Tips: - Revisit as you go! As the work progresses, things will naturally shift. This lets you keep track of where you are (and where you might need more time). - Pay attention to how many blocks each person has per week.
Note on A11: Steps are the specific actions that make up the stream. Get specific and include buffers and mini mitigation plans. Tips: - Note differences between internal and must-achieve by/external deadlines. - Include getting input from stakeholders. - Your steps might have dependencies (a specific sequence in which they have to happen), so try to write them in chronological order. - If you anticipate risks, name them.
Note on C11: The person responsible for the success or failure of the step/task.
Note on D11: The person/people being reached out to for input, buy-in, or (sometimes) approval.
Note on F11: Start at the end (when you know the project needs to be done by), then work backwards.
Note on G11: Review this column at project update meetings. The "stuck" option is for flagging a need for help from someone else. Spend less time at meetings on updates and more time on mitigating roadblocks.
Note on H11: Use this row for important dates that may impact people's availability or capacity.