## READ ME
About this Tool
The Red Light/Green Light Goal Tracking Tool is for tracking progress toward goals. This resource contains samples of goals at the organizational, team, and individual levels. We recommend using it once you’ve finalized your goals and revisiting at regular intervals (monthly, quarterly, etc.) to check in on progress.
For organizational leaders, you might use this tool to keep track of your organizational and team goals (using one tab per team!) in one place.
For team/department leaders, you can keep track of your team goals and use separate tabs for each person you manage.
For individuals, use this to keep track of your own goals (or add a tab for your team goals, for reference).

## Organizational Sample
Note: There are multiple sheets within this tool—click through the tabs at the bottom of the spreadsheet.
|  | Organizational Goals |  |  | Stepback
Priority Area | Goal | Tactics (or Benchmarks / Metrics) | Owner | Current Status | Q1 Update (4/1) | Q2 Update (as of mm/dd) | Q3 Update (as of mm/dd) | Q4 Update (as of mm/dd)
This can be a word (like "Impact") or a sentence ("Be the go-to resource on XYZ issue") that captures what you're trying to achieve with your goals. We recommend limiting the total number of organizational priorities to 5. | Your goal should be SMARTIE: Strategic, Measurable, Ambitious, Realistic, Time-bound, Inclusive, and Equitable. At minimum, your statement should capture the "measurable" and "time-bound" aspects of the goal. | Identify key tactics you will use or benchmarks/metrics you will hit to achieve the goal. If your goal statement alone doesn't capture the "inclusive" and "equitable" aspects of your goal, specify how you're mitigating disparate impact or advancing equity and inclusion in your tactics, benchmarks, or metrics. | The person or team responsible for achieving the goal. Note that organizational goals default to being "owned" by the executive or senior leadership team unless otherwise specified. | On track: Likely to achieve this goal or already completed Not started yet: Have not started making progress yet Not on track: Significantly behind or off track | Indicate when you will review progress quarterly (or monthly or biannually). You can also add columns to indicate benchmarks for each period. Revisit at regular intervals to share updates/progress toward goals.
SUSTAINABILITY | Raise $2M by end of year to cover this year’s budget and 3 months’ operating reserve. | - Explore option of creating small donor program to engage members from lower-income backgrounds, with a goal of C6 our membership in this demographic by 25% - Apply for 3 new grants and 5 renewals - Explore partnerships with companies that align with our values, particularly around equity, inclusion, and antiracism | Rafael (Development Director) | On track | We have raised $1M to date and are ahead of our pacing.
IMPACT | Grow the grassroots power of our membership base. By end of year, at least 2,500 people (of which 40% identify as BIPOC) will have been trained through our leadership development programs. At least 80% of participants will answer yes to the statement: "I would recommend this program to a friend." [Cross-listed under Program Team goals] | - Reach out to alumni network for training referrals and nominees - Partner with local organizations to identify potential candidates - Continue building relationship with local HBCU | Anique (Program Director) | Not started yet | We should have enough trainings scheduled in the second half of the year to hit our overall goal, but need to do additional outreach to get to 40% BIPOC.
IMPACT | Strengthen housing rights coalition and broaden our reach by recruiting 3 local organizations to join by June. These organizations should work with communities that are not currently represented in the coalition. [Cross-listed under Program Team goals] | - Have 1-1s with leaders of community-based organizations - Create 2-pager for coalition recruitment efforts - Host community events for networking and publicity | Anique | On track | Five target organizations have been identified and we've created an outreach and relationship-building plan.
SUSTAINABILITY | Fill all open roles by June 20xx, with pools for each role having at least XX% BIPOC candidates. | - Host quarterly informational sessions for potential candidates - Join X network and conduct 1-1s to build our pool of candidates and connectors | Mimi (Head of Talent) | Not on track | Program Team hires are going well, but Finance Team hiring hasn't gotten off the ground yet because this year's audit is more complicated than expected. If hiring hasn't started by end of Q2, we may need to adjust the goal or focus on finding temp work to fill gaps.
©The Management Center

## Team Sample
Note: There are multiple sheets within this tool—click through the tabs at the bottom of the spreadsheet.
|  | Program Team Goals |  |  | Stepback
Priority Area | Goal | Tactics (or Benchmarks / Metrics) | Owner | Current Status | Q1 Update (4/1) | Q2 Update (as of mm/dd) | Q3 Update (as of mm/dd) | Q4 Update (as of mm/dd)
Share the organizational priority the goal is connected to. You can also group goals into buckets of work and specify them. For example, if your team's buckets of work include leadership development and partnerships, you could write: "Impact: leadership development." | Your goal should be SMARTIE: Strategic, Measurable, Ambitious, Realistic, Time-bound, Inclusive, and Equitable. At minimum, your statement should capture the "measurable" and "time-bound" aspects of the goal. | Identify tactics you will use or benchmarks/metrics you will hit to achieve the goal. If your goal statement alone doesn't capture the "inclusive" and "equitable" aspects of your goal, specify how you're mitigating disparate impact or advancing equity and inclusion in your tactics, benchmarks, or metrics. | The person or team responsible for the goal. | On track: Likely to achieve this goal or already completed Not started yet: Have not started making progress yet Not on track: Significantly behind or off track | Indicate when you will review progress quarterly (or monthly or biannually). You can also add columns to indicate benchmarks for each period. Revisit at regular intervals to share updates/progress toward goals.
IMPACT: Leadership Development | Grow the grassroots power of our membership base. By end of year, at least 2,500 people (of which 40% identify as BIPOC) will have been trained through our leadership development programs. At least 80% of participants will answer yes to the statement: "I would recommend this program to a friend." [Cross-listed under organizational goals] | - Reach out to alumni network for referrals and nominees - Partner with local organizations to identify potential candidates - Continue building relationship with local HBCU | Anique (Program Director) | Not started yet | We should have enough trainings scheduled in the second half of the year to hit our overall goal, but need to do additional outreach to get to 40% BIPOC.
IMPACT: Partnerships & Coalition | Strengthen housing rights coalition and broaden our reach by recruiting 3 local organizations to join by June. These organizations should work with communities that are not currently represented in the coalition. [Cross-listed under organizational goals] | - Have 1-1s with leaders of community-based organizations - Create 2-pager for coalition recruitment efforts - Host 3 community events to publicize coalition | Anique | On track | Five target organizations have been identified and we've created an outreach and relationship-building plan. | We have connected with three target organizations—2 soft yeses, 1 maybe. Follow-ups have been scheduled.
SUSTAINABILITY: Capacity | Fill Program Associate vacancy by May 20xx. [As part of organizational goal: Fill all open roles by June 20xx, with pools for each role having at least XX% BIPOC candidates.] | - Reach out to Maria from XYZ network - Reach out to alumni network and identify 5 connectors and/or candidates, of which 80% should be BIPOC. | Jia Ying (Program Manager) | On track | Job announcement shared at end of January—pool is currently at 50% BIPOC, 30% LGBTQ. Just started 2nd round interviews. We may be on track to have new hires begin onboarding by mid-April.
©The Management Center

## Individual Sample
Note: There are multiple sheets within this tool—click through the tabs at the bottom of the spreadsheet.
|  | Program Manager Goals |  |  |  | Stepback
Priority Area | Goal | Alignment with team or organizational goal | Tactics (or Benchmarks / Metrics) | Additional Notes (MOCHA, considerations, tasks, etc.) | Current Status | Q1 Update (4/1) | Q2 Update (as of mm/dd) | Q3 Update (as of mm/dd) | Q4 Update (as of mm/dd)
Share the organizational priority the goal is connected to. You can also group goals into buckets of work and specify them. For example, if your team's buckets of work include leadership development and partnerships, you could write: "Impact: leadership development." | Your goal should be SMARTIE: Strategic, Measurable, Ambitious, Realistic, Time-bound, Inclusive, and Equitable. At minimum, your statement should capture the "measurable" and "time-bound" aspects of the goal. | Specify which team or organizational goal your individual goal is connected to. | Identify key tactics you will use or benchmarks/metrics you will hit to achieve the goal. If your goal statement alone doesn't capture the "inclusive" and "equitable" aspects of your goal, specify how you're mitigating disparate impact or advancing equity and inclusion in your tactics, benchmarks, or metrics. | Include any information that will help you achieve your goal, such as the MOCHA (especially helpers, consulteds and approvers), considerations, and important tasks. | On track: Likely to achieve this goal or already completed Not started yet: Have not started making progress yet Not on track: Significantly behind or off track | Indicate when you will review progress quarterly (or monthly or biannually). You can also add columns to indicate benchmarks for each period. Revisit at regular intervals to share updates/progress toward goals.
IMPACT: Leadership Development | Improve average participant experience scores from 60% highly satisfied to 65% highly satisfied, with no disparities in race or gender. | Organizational/Team goal: Grow the grassroots power of our membership base. By end of year, at least 2,500 people (of which 40% identify as BIPOC) will have been trained through our leadership development programs. At least 80% of participants will answer yes to the statement: "I would recommend this program to a friend." | - Solicit feedback from last year's BIPOC alum on programming logistics through surveys, 1-1s, and focus groups. - Experiment with new platform for participant engagement during the course of the program. - Work with curriculum lead to align curriculum changes with logistical needs. | C: Make sure to have a 1-1 with Lyle. H: Ask Karla for supporting reaching out to some alum. A: Share plan with Anique by Apr 1 | Not started yet | We've solicited feedback, but haven't decided on what changes to test. If we can start testing by May 1, we should be on track to meet this goal.
IMPACT: Partnerships & Coalition | Recruit members of target organizations to attend at least one of three community events in March. | Organizational/Team goal: Strengthen housing rights coalition and broaden our reach by recruiting 3 local organizations to join by June. These organizations should work with communities that are not currently represented in the coalition. | - Conduct 1-1s with members and staff of target organizations - Reach out to connectors to put in a good word about our work |  | On track
SUSTAINABILITY: Capacity | Fill Program Associate vacancy by May 20xx. | Organizational goal: Fill all open roles by June 20xx, with pools for each role having at least XX% BIPOC candidates. Team goal: Fill Program Associate vacancy by May 20xx. | - Reach out to Maria from XYZ network - Reach out to alumni network and identify 5 connectors and/or candidates, of which 80% should be BIPOC. | Start tracking potential future talent. Consult with Mimi. | On track | Job announcement shared at end of January—pool is currently at 50% BIPOC, 30% LGBTQ. Just started 2nd round interviews. We may be on track to have new hires begin onboarding by mid-April.
©The Management Center