# Project Plan: Unionization Phases One and Two

### About This Resource This toolkit is part of a resource collection for leaders and managers preparing for a unionization process. This toolkit helps senior leaders plan the first two phases of unionization: 1) recognition and 2) preparing for bargaining. It contains: - Sample language for defining success for the unionization process overall, and the first two phases specifically - Sample project plans for each phase (adapted from TMC’s Project Plan Template & Sample tool) Note that the streams in the project plan samples have no set timeline—but they do need to happen before bargaining begins. Once the union announces its intention to seek recognition, management should tackle these areas of work as quickly as possible. If you’re not yet familiar with the phases of unionization, check out Beyond Neutrality’s overview before you jump into this project plan.

| Project: | Phases One & Two of Unionization: recognition request up until bargaining begins |
| --- | --- |

The unionization process will be a success if we:

- Arrive at a Collective Bargaining Agreement that is satisfactory to both the union and management.

- Balance timeliness with care, intentionality, and thoroughness.

- Uphold our organizational values and the Beyond Neutrality approach throughout the process.

- Keep [organization]’s mission and vision at the forefront.

Phase one (recognition) will be successful if we:

- Arrive at a voluntary recognition agreement that is acceptable to the union and management.

- Train and educate managers and leaders on the unionization process.

- Secure a pro-union management-side attorney and consultant(s).

- Ground managers in the Guiding Principles.

Phase two (preparing for bargaining) will be successful if we:

- Are confident and ready to go on the first day of bargaining.

- Have a trained and prepared Management Bargaining Team (MBT), and all managers trained in what to expect in bargaining.

- Have communicated effectively and in good faith with the union.

- Have all the information we need about our policies, practices, and finances, and have identified similar organizations for comparison.

We will coordinate and communicate along the way as follows:

- The [Senior Leadership / Executive Team], driven by the [Chief of Staff / Managing Director / Executive Director], will own the initial tasks of each project plan until the MBT is established.

- The MBT operating agreement will determine who is in the MBT, what their individual roles and responsibilities will be, and how decisions will be made within that body. Note: no decisions made by the MBT are final; final decisions are made through the bargaining process.

# Project Plan Samples

For the purposes of these samples, we used common placeholder titles for senior roles at nonprofit organizations. Your organization may use different titles, and/or senior leadership may choose a different person or people to own these various pieces of the project.

## Phase One: Recognition Phase

| Area of Work (“Stream”) | Steps | Due Date | Stakeholders / MOCHA | Status / Notes |
| --- | --- | --- | --- | --- |
| Overall project management | Manage ongoing coordination with the Senior Leadership Team. | Ongoing | Owner: Chief of Staff Helpers: Executive Director, Chief Financial Officer |  |
|  | Establish MOCHAs & 5Ws for each Stream. | ASAP | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
| Set up management systems and structures | Secure pro-union attorney for advice on the Voluntary Recognition process. Secure consultant(s) for support with managing during the unionization process. | ASAP | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
| Support and training for managers | Set up unionization training for managers. | Before Bargaining Begins | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
| Gather necessary information | Speak to leaders from other recently unionized organizations. | Before Bargaining Begins | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
|  | Read through Beyond Neutrality Resource Hub. | Before Bargaining Begins | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
| Coordination with the union | Communicate with all employees (including union) support for the rights of employees to unionize. | Before Voluntary Recognition | Owner: Chief of Staff Helpers: Executive Director, Chief Financial Officer, attorney |  |
|  | Oversee the steps of voluntary recognition. | Before Voluntary Recognition | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |

## Phase Two: Preparing for Bargaining

| Area of Work (“Stream”) | Steps | Due Date | Stakeholders / MOCHA | Status / Notes |
| --- | --- | --- | --- | --- |
| Overall project management | Manage ongoing coordination with the Senior Leadership Team. | Ongoing | Owner: Chief of Staff Helpers: Executive Director, Chief Financial Officer |  |
|  | Align and/or deconflict internal DEI work with bargaining. | Ongoing | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
| Set up management systems and structures | Align Senior Leadership Team on unionization tasks roles, goals, and ongoing coordination. | ASAP | Owner: Chief of Staff Helpers: Executive Director, Chief Financial Officer |  |
|  | Select MBT members. | Before Bargaining Begins | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
|  | Convene MBT to review and finalize the Operating Agreement. | Before Bargaining Begins | Owner: Lead Negotiator Helpers: Bargaining Team Members, Attorney, Consultant(s) |  |
| Support and training for managers | Support facilitation of unionization training for managers and schedule any follow-up sessions. | Before Bargaining Begins | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
|  | Establish manager engagement plan and schedule manager meetings. | Before Bargaining Begins | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
| Gather necessary information | Listen to input from managers and other non-unit staff. | Before Bargaining Begins | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
|  | Review contracts from other union organizations, ask peers for lessons learned. | Before Bargaining Begins | Owner: Chief of Staff Helpers: Senior Leadership Team, senior managers |  |
|  | Compile internal policy, salary, and benefit information. | Before Bargaining Begins | Owner: TBD within MBT Helpers: - Financial Information: Chief Financial Officer - Benefits Information: Human Resources Director |  |
|  | Begin financial analysis and identify management priorities for spending. | Before Bargaining Begins |  |  |
| Coordination with the union | Furnish information requests. | Ongoing | Owner: TBD within Senior Leadership Team, then MBT once established Helpers: Attorney, Management Bargaining Team Members |  |
|  | Send email to all staff announcing the recognition agreement and intent to bargain. | Ongoing | Owner: TBD within MBT Helpers: Management and Union Bargaining Team Members, Attorney, Consultant(s) |  |
|  | Discuss handling of issues during status quo period, possibility of joint communication to all staff and/or joint training of bargaining committees, and a tentative timeline for bargaining to begin. | Before Bargaining begins | Owner: TBD within MBT Helpers: Management and Union Bargaining Team Members, Attorney, Consultant(s) |  |
|  | Determine logistics for negotiations, including: ground rules, bargaining style, modes of communication, and bargaining schedule. | Closer to bargaining, but before it begins | Owner: TBD within MBT Helpers: Management and Union Bargaining Team Members, Attorney, Consultant(s) |  |